Signal Workshop / Client proposal delivery brief
Prepared by Northline Design for Signal Workshop
Illustrative draft. Client decisions, fees and commitments require review.
	Issued
	Review by
	Proposed start

	2026-10-09
	2026-10-16
	2026-10-19



Project context
Fictional Signal Workshop project. Compare reviewed page, launch and creative handoff scopes. All fees and commitments are illustrative.
Proposed outcomes
Help a visitor understand which workflow fits their task.
Give the launch a consistent visual and editorial direction.
Define a reviewable handoff for creative files and measurement.
Focus
Clarify the story and make the next click understandable.
Planned duration in calendar weeks: 3. Estimated investment USD 950.00.
Prepared by Northline Design: Fictional team / replace before client delivery. For Signal Workshop: Fictional client / no external recipient.
Source SHA-256: 23ce90701ee47985cf5e18eaddea087bd336bc6987189255831b6143138981e5
Delivery scope
Editorial story map
A message hierarchy and page outline grounded in the supplied product references. Proposed messages remain drafts until reviewed.
Owner Studio editor. Planned 2026-10-19 to 2026-10-25. Requirements clear-story.
Acceptance: Map each proposed message to a supplied reference.
Review the page outline and one round of copy revisions.
Launch page system
A responsive introduction, workflow explanation and publishing handoff using the approved story map.
Owner Studio designer. Planned 2026-10-26 to 2026-11-08. Requirements clear-story, coordinated-launch.
Acceptance: Review the three page states at desktop and mobile widths.
Deliver editable source and a publishing checklist.
Focus investment and schedule
Clarify the story and make the next click understandable.
	Budget item
	Qty
	Unit price
	Amount

	Story and message hierarchy
	1
	USD 500.00
	USD 500.00

	Responsive page system
	1
	USD 450.00
	USD 450.00



Subtotal USD 950.00. Discount 0%: USD 0.00. Net after discount USD 950.00.
Supplied tax 0%: USD 0.00.
Estimated total USD 950.00
Proposed payment milestones
	Stage
	Share
	Amount
	Trigger

	Kickoff
	40%
	USD 380.00
	After scope and dates are agreed

	Draft review
	40%
	USD 380.00
	After the agreed draft is presented

	Final handoff
	20%
	USD 190.00
	After the agreed acceptance review



Planned calendar
	Deliverable
	Owner
	From
	To

	Editorial story map
	Studio editor
	2026-10-19
	2026-10-25

	Launch page system
	Studio designer
	2026-10-26
	2026-11-08



Planned calendar weeks of seven days from startDate; no business-day or holiday adjustment.
Requirements outside this option: creative-system, measurement
Requirements and evidence
clear-story
Explain the value of a tested, editable workflow with concrete first-run examples.
Supplied sources: catalog
coordinated-launch
Carry the product story across launch pages and social cards.
Supplied sources: catalog, carousel
creative-system
Create a coherent motion and visual direction for future editorial releases.
Supplied sources: motion, carousel
measurement
Define the events and review questions needed to evaluate the launch; current conversion measurements are not supplied.
Supplied sources: catalog
catalog | Signal Workshop / authored practice brief | examples/proposal.json / authored practice facts
motion | Fictional creative request | Client requests one short collection film
carousel | Fictional brand brief | Client requests six cards with editable artwork
Assumptions and exclusions
Assumptions
The client, studio, facts and fees are fictional practice material.
The client provides source copy and asset rights before the proposed start.
One consolidated review round is included per deliverable. Calendar dates remain tentative until availability is confirmed.
Excluded work
Paid media spend, production hosting and third-party subscriptions.
Authentication, payment implementation and external publishing.
Claims of sales, growth or conversion improvement without measured evidence.
Next steps
Select the scope that matches the current priority.
Confirm uncovered requirements, supplied tax treatment and the illustrative fee structure.
Agree owners and dates, then issue a separate approved engagement document.
Calculation policy: ROUND_HALF_UP each quantity × unit price to cents; discount on subtotal; tax on discounted net; largest remainder stages with input-order ties.
Proposal draft  |  




