# Signal Workshop / Client proposal

Prepared by Northline Design for Signal Workshop

Illustrative draft. Client decisions, fees and commitments require review.

| Issued | Review by | Proposed start |
| --- | --- | --- |
| 2026-10-09 | 2026-10-16 | 2026-10-19 |

# Project context

Fictional Signal Workshop project. Compare reviewed page, launch and creative handoff scopes. All fees and commitments are illustrative.

## Proposed outcomes

Help a visitor understand which workflow fits their task.

Give the launch a consistent visual and editorial direction.

Define a reviewable handoff for creative files and measurement.

## Options at a glance

| Option | Scope | Weeks | Total |
| --- | --- | --- | --- |
| Focus | 2 deliverables | 3 | USD 950.00 |
| Launch | 3 deliverables | 3 | USD 1,221.00 |
| Studio | 5 deliverables | 4 | USD 2,700.00 |

Prepared by Northline Design: Fictional team / replace before client delivery. For Signal Workshop: Fictional client / no external recipient.

Source SHA-256: 23ce90701ee47985cf5e18eaddea087bd336bc6987189255831b6143138981e5

# Delivery library

## Editorial story map

A message hierarchy and page outline grounded in the supplied product references. Proposed messages remain drafts until reviewed.

Owner Studio editor. Planned 2026-10-19 to 2026-10-25. Requirements clear-story.

Acceptance: Map each proposed message to a supplied reference.

Review the page outline and one round of copy revisions.

## Launch page system

A responsive introduction, workflow explanation and publishing handoff using the approved story map.

Owner Studio designer. Planned 2026-10-26 to 2026-11-08. Requirements clear-story, coordinated-launch.

Acceptance: Review the three page states at desktop and mobile widths.

Deliver editable source and a publishing checklist.

## Branded social carousel

Six editorial cards in portrait, square and wide formats, with editable artwork and a proposed posting order.

Owner Studio designer. Planned 2026-11-02 to 2026-11-08. Requirements coordinated-launch, creative-system.

Acceptance: Inspect every exported card for text fit.

Deliver PNG and editable SVG with brand tokens.

## Editorial motion story

A proposed 30-second collection film in three canvas formats, with an editable storyboard and caption files.

Owner Motion designer. Planned 2026-11-02 to 2026-11-15. Requirements creative-system.

Acceptance: Review narrative and a draft before final rendering.

Inspect all three videos and hand over the storyboard.

## Measurement handoff

A draft event contract and launch review checklist. Instrumentation, traffic collection and performance claims are outside this quote.

Owner Product analyst. Planned 2026-11-09 to 2026-11-15. Requirements measurement.

Acceptance: Review event names, deduplication and review windows.

Record unknown baselines explicitly.

# Focus investment and schedule

Clarify the story and make the next click understandable.

| Budget item | Qty | Unit price | Amount |
| --- | --- | --- | --- |
| Story and message hierarchy | 1 | USD 500.00 | USD 500.00 |
| Responsive page system | 1 | USD 450.00 | USD 450.00 |

Subtotal USD 950.00. Discount 0%: USD 0.00. Net after discount USD 950.00.

Supplied tax 0%: USD 0.00.

## Estimated total USD 950.00

## Proposed payment milestones

| Stage | Share | Amount | Trigger |
| --- | --- | --- | --- |
| Kickoff | 40% | USD 380.00 | After scope and dates are agreed |
| Draft review | 40% | USD 380.00 | After the agreed draft is presented |
| Final handoff | 20% | USD 190.00 | After the agreed acceptance review |

## Planned calendar

| Deliverable | Owner | From | To |
| --- | --- | --- | --- |
| Editorial story map | Studio editor | 2026-10-19 | 2026-10-25 |
| Launch page system | Studio designer | 2026-10-26 | 2026-11-08 |

Planned calendar weeks of seven days from startDate; no business-day or holiday adjustment.

Requirements outside this option: creative-system, measurement

# Launch investment and schedule

Add a coordinated social sequence to the page system.

| Budget item | Qty | Unit price | Amount |
| --- | --- | --- | --- |
| Story and message hierarchy | 1 | USD 300.00 | USD 300.00 |
| Responsive page system | 1 | USD 450.00 | USD 450.00 |
| Six-card creative set | 1 | USD 350.00 | USD 350.00 |

Subtotal USD 1,100.00. Discount 7.5%: USD 82.50. Net after discount USD 1,017.50.

Supplied tax 20%: USD 203.50.

## Estimated total USD 1,221.00

## Proposed payment milestones

| Stage | Share | Amount | Trigger |
| --- | --- | --- | --- |
| Kickoff | 40% | USD 488.40 | After scope and dates are agreed |
| Draft review | 40% | USD 488.40 | After the agreed draft is presented |
| Final handoff | 20% | USD 244.20 | After the agreed acceptance review |

## Planned calendar

| Deliverable | Owner | From | To |
| --- | --- | --- | --- |
| Editorial story map | Studio editor | 2026-10-19 | 2026-10-25 |
| Launch page system | Studio designer | 2026-10-26 | 2026-11-08 |
| Branded social carousel | Studio designer | 2026-11-02 | 2026-11-08 |

Planned calendar weeks of seven days from startDate; no business-day or holiday adjustment.

Requirements outside this option: measurement

# Studio investment and schedule

Build the complete editorial, motion and measurement handoff.

| Budget item | Qty | Unit price | Amount |
| --- | --- | --- | --- |
| Story and message hierarchy | 1 | USD 300.00 | USD 300.00 |
| Responsive page system | 1 | USD 450.00 | USD 450.00 |
| Six-card creative set | 1 | USD 350.00 | USD 350.00 |
| Three-format motion story | 1 | USD 850.00 | USD 850.00 |
| Measurement specification | 1 | USD 300.00 | USD 300.00 |

Subtotal USD 2,250.00. Discount 0%: USD 0.00. Net after discount USD 2,250.00.

Supplied tax 20%: USD 450.00.

## Estimated total USD 2,700.00

## Proposed payment milestones

| Stage | Share | Amount | Trigger |
| --- | --- | --- | --- |
| Kickoff | 40% | USD 1,080.00 | After scope and dates are agreed |
| Draft review | 40% | USD 1,080.00 | After the agreed draft is presented |
| Final handoff | 20% | USD 540.00 | After the agreed acceptance review |

## Planned calendar

| Deliverable | Owner | From | To |
| --- | --- | --- | --- |
| Editorial story map | Studio editor | 2026-10-19 | 2026-10-25 |
| Launch page system | Studio designer | 2026-10-26 | 2026-11-08 |
| Branded social carousel | Studio designer | 2026-11-02 | 2026-11-08 |
| Editorial motion story | Motion designer | 2026-11-02 | 2026-11-15 |
| Measurement handoff | Product analyst | 2026-11-09 | 2026-11-15 |

Planned calendar weeks of seven days from startDate; no business-day or holiday adjustment.

Requirements outside this option: None in the supplied brief

# Requirements and evidence

## clear-story

Explain the value of a tested, editable workflow with concrete first-run examples.

Supplied sources: catalog

## coordinated-launch

Carry the product story across launch pages and social cards.

Supplied sources: catalog, carousel

## creative-system

Create a coherent motion and visual direction for future editorial releases.

Supplied sources: motion, carousel

## measurement

Define the events and review questions needed to evaluate the launch; current conversion measurements are not supplied.

Supplied sources: catalog

catalog | Signal Workshop / authored practice brief | examples/proposal.json / authored practice facts

motion | Fictional creative request | Client requests one short collection film

carousel | Fictional brand brief | Client requests six cards with editable artwork

# Assumptions and exclusions

## Assumptions

The client, studio, facts and fees are fictional practice material.

The client provides source copy and asset rights before the proposed start.

One consolidated review round is included per deliverable. Calendar dates remain tentative until availability is confirmed.

## Excluded work

Paid media spend, production hosting and third-party subscriptions.

Authentication, payment implementation and external publishing.

Claims of sales, growth or conversion improvement without measured evidence.

## Next steps

Select the scope that matches the current priority.

Confirm uncovered requirements, supplied tax treatment and the illustrative fee structure.

Agree owners and dates, then issue a separate approved engagement document.

Calculation policy: ROUND_HALF_UP each quantity × unit price to cents; discount on subtotal; tax on discounted net; largest remainder stages with input-order ties.